## Contractor Work Order
Contractor Work Order
Issue work to an external contractor, agree the price before it starts, and accept the work before the invoice is approved.
✦ Part A — Before work starts
1. Work order details
Work order number e.g. CWO-2026-0148
Date raised
Raised by (name and role)
Site / property
Building, floor or area
Asset or equipment reference
Priority Emergency / Urgent / Routine / Planned
Required start date
Required completion date
2. Contractor details
Contractor company
Trade or discipline e.g. Mechanical, Electrical, Fabric, Lifts
Contact name
Phone
Email
Contractor's own reference
Purchase order number
Framework or contract reference
3. Agreed scope of work
Work to be carried out
Specifically excluded from this order
Access arrangements and site hours
Permits required Hot work / Confined space / Electrical isolation / Working at height / None
Isolations or shutdowns needed
Materials supplied by client
4. Compliance checks before mobilisation
Check |  |  | Done | Evidence reference |  | Verified by | Date
Public liability insurance in date |  |  | ☐
Employer's liability insurance in date |  |  | ☐
Professional indemnity in date (if applicable) |  |  | ☐
RAMS received and approved |  |  | ☐
Permit to work issued |  |  | ☐
Site induction completed |  |  | ☐
Competency or trade certification verified |  |  | ☐
Sub-contractors declared and approved |  |  | ☐
✦ Work should not be released until every line above is complete. A missing RAMS is the single most common reason a contractor invoice is disputed after an incident.
✦ Part B — The money
5. Agreed price
Line | Description of work or material |  |  | Qty | Unit | Rate | Amount
1 | Replace AHU-03 supply fan bearings, labour |  |  | 6 | hours | 48 | 288
Agreed price subtotal | [6 empty] | 288
6. Variations
Ref | Date | Reason for variation |  |  |  | Approved by | Agreed cost
V1 | 14/09/2026 | Corroded pipework found behind panel, additional 2m replacement |  |  |  | R. Mehta | 165
Variations total | [6 empty] | 165
✦ A variation agreed by phone and not written here is the variation that gets argued about at invoice stage.
7. Order value summary
Agreed price subtotal |  |  |  |  | 288
Variations total |  |  |  |  | 165
Subtotal |  |  |  |  | 453
Retention rate (%) e.g. 5
Retention held |  |  |  |  | 0
Tax / VAT rate (%) e.g. 20
Tax / VAT |  |  |  |  | 0
Total payable on this order |  |  |  |  | 453
✦ Part C — Completion, acceptance and invoice
8. Work completed
Actual start date
Actual completion date
Work carried out
Parts and materials supplied by contractor
Waste removed and disposal reference
Site left safe and clean Yes / No
Test certificates or commissioning records issued Yes / No / Not applicable
Warranty period on this work
9. Work acceptance
Acceptance decision Accepted / Accepted with defects / Rejected
Defects or outstanding items
Date defects to be cleared by
Accepted by (name)
Role
Signature
Date accepted
✦ Do not approve an invoice against this order until this section is signed. Acceptance is the control — an invoice approved before acceptance removes the only leverage you have to get defects cleared.
10. Invoice
Contractor invoice number
Invoice date
Invoice value
Matches order value above Yes / No
If no, variance and reason
Retention released Yes / No / Date due
Approved for payment by
Date approved
11. Notes

## How to use
Contractor Work Order
How to use this file
1. Fill the white cells. Grey cells calculate themselves — do not type in them.
2. Enter the agreed price on the Work Order tab before the contractor mobilises. The subtotal, retention and tax update as you type.
3. Record every variation on its own row with a reason and an approver. Variations feed the order value summary automatically.
4. Set the retention and tax rates as percentages — enter 5, not 0.05.
5. Sign section 9 before approving the invoice in section 10.
6. Use the Job Log tab if you run a rolling file rather than one document per job.
Key
White cell with a border | You type here
Grey cell | Calculated — leave it alone
Grey italic row | Worked example showing the expected format
Every field in this workbook also appears in the Word and PDF versions of this template. The Job Log tab is the one addition, for teams who keep a running file rather than a document per job.

## Job Log
WO number | Date raised | Site | Contractor | Trade | PO number | Scope summary | Agreed price | Variations | Order total | Accepted (Y/N) | Date accepted | Invoice number | Invoice value | Variance | Status
CWO-2026-0148 | 12/09/2026 | Northgate House | Brightwell M&E | Mechanical | PO-88214 | AHU-03 fan bearing replacement | 288 | 165 | 453 | Y | 18/09/2026 | INV-4471 | 453 | 0 | Paid
Total | [6 empty] | 0 | 0 | 0 |  |  |  | 0 | 0
One row per contractor work order, for teams who keep a running file rather than a document per job. The example row is grey italic — overwrite it or delete it.