## Work Order
Maintenance Work Order
Job record and completion sign-off
How to use this sheet
✦ | Fill in the job details before the work starts, and the rest on the visit.
✦ | Copy the asset ID off the tag on the equipment, not from memory.
✦ | Grey cells calculate themselves. Everything else is yours to type in.
✦ | Keep the reported fault separate from what you actually found.
✦ | Use the Job log sheet if you'd rather keep one running file than a document per job.
Job details
Work order no. |  |  |  | WO-0000
Date raised |  |  |  | __ / __ / ____
Raised by
Priority |  |  |  | Low / Med / High / Urgent
Site / building
Location
Asset ID
Asset name
Work type |  |  |  | Corrective / PM / Inspection
Assigned to
Reported fault
Target completion |  |  |  | __ / __ / ____
Downtime
The number operations asks for, and the one most maintenance logs leave out.
Asset out of service |  |  |  | __ / __ / ____ __ : __
Back in service |  |  |  | __ / __ / ____ __ : __
Total downtime (hrs)
Work performed
What was reported goes above. What you actually found and did goes here.
# | Work performed | [5 empty] | Done |  | Hrs | Notes
1 | Attend site and confirm the reported fault
2 | Isolate the asset and apply lockout/tagout
3 | Record asset condition and meter reading
4 | Carry out the repair or scheduled task
5 | Replace consumables and log parts used
6 | Function-test and confirm the fault cleared
7 | Remove isolation and return to service
8 | Clear the work area and remove waste
9
10
11
12
13
14
15
16
17
18
19
20
Total hours on tasks
Parts and materials used
Part no. |  | Description |  |  |  |  | Qty | Unit cost |  | Line total
FLT-2040 |  | Air filter, 20 x 40 |  |  |  |  | 2 | 18.5 |  | 37
Parts subtotal | [9 empty] | 37
Labour
Name |  |  | Trade / role |  |  | Hours | Rate |  | Cost
A. Technician |  |  | HVAC |  |  | 2.5 | 45 |  | 112.5
Labour subtotal | [8 empty] | 112.5
Job cost
Parts subtotal | [8 empty] | 37
Labour subtotal | [8 empty] | 112.5
Total job cost | [8 empty] | 149.5
Cause and follow-up
Root cause found
Fault cleared |  |  |  |  | Yes / No
Follow-up work needed |  |  |  |  | Yes / No New work order no. ____________
Parts to reorder
Sign-off
The technician's signature says the work is done. The acceptor's says someone else agrees. Only the second one closes the job.
Carried out by (technician)
Name |  |  |  |  | Signature |  |  |  | Date
Accepted by (supervisor / client)
Name |  |  |  |  | Signature |  |  |  | Date
Closed and filed by
Name | [8 empty] | Date
Free to use, edit and rebrand. No attribution required. facilio.com/templates/maintenance-work-order/

## Job log
Job log
One row per work order. Use this if you'd rather keep a running log than a document per job.
WO no. | Date raised | Asset ID | Asset name | Work type | Priority | Reported fault | Assigned to | Date completed | Downtime hrs | Labour hrs | Parts cost | Labour cost | Total cost | Status
WO-0412 | 2026-08-03 | AHU-04 | Air handling unit 4 | Corrective | High | No cooling on second floor | A. Technician | 2026-08-03 | 3.5 | 2.5 | 37 | 112.5 | 149.5 | Closed
[8 empty] | Totals | 3.5 | 2.5 | 37 | 112.5 | 149.5